## CallPilot Installer Roadmap
CallPilot 4.0
Installer's
Roadmap
Avaya CallPilot® 5.0 Installer Roadmap
Document Number: NN44200-319 |  | Version: 01.04
December 2010
Project # / Contract #
Customer
Address
Project Manager / Leader

## Revision History
Revision History
Version Number | Date | Revision | Author
Standard 01.04 | December, 2010 | CallPilot 5.0, Standard 01.03. Issued for SU09 Launch Approval. | Karrie Anderson
Standard 01.04 | November, 2010 | CallPilot 5.0, Standard 01.04. Rebranded | Tammy Crowley
Standard 01.03 | 2010-07-29 | CallPilot 5.0, Standard 01.03. Issued for SU08 General Availability | Karrie Anderson
Draft 01.BA | 2010-06-06 | CallPilot 5.0, Draft 01.BA. Issued for SU08 Beta | Karrie Anderson
Standard 01.01 | 2009-01-24 | CallPilot 5.0, Standard 01.0 Issued for General Availability. | Dawn Roy
Copyright © 2010 Avaya. All Rights Reserved. Terms of Use: The information and/or products described in this document are subject to change without notice. While the information in this document is believed to be accurate and reliable, AVAYA PROVIDES THIS DOCUMENT "AS IS" WITHOUT WARRANTY OR CONDITION OF ANY KIND, EITHER EXPRESS OR IMPLIED, INCLUDING, BUT NOT LIMITED TO, THE IMPLIED WARRANTIES OR CONDITIONS OF MERCHANTABILITY, FITNESS FOR A PARTICULAR PURPOSE OR NON-INFRINGEMENT. The information in this document could include technical inaccuracies or typographical errors. Trademarks Avaya and the Avaya logo are trademarks of Avaya.

## Customer & Site
Customer and Site Information
|  |  |  | 0 | 0
To be completed and verified during coordination conference calls.
Installation Coordinator is responsible for forwarding copies of this document to parties involved with installation.
Completed by home office
Site ID #
Purchase order# |  | Requested install date:
Clarify ticket # |  | Date of walkthrough
Customer name:
Customer contact name 1: |  | Contact 1 phone#:
Ship To Address |  | Contact 1 fax#:
(if different than customer address) |  | Contact 1 pager#:
Contact 1 e-mail address:
Database contact: |  | Dbase phone#:
Dbase fax#:
Dbase pager#:
Dbase e-mail address:
Customer address:
Address line 2:
City: | State: |  | Zipcode:
LAN administrator: |  | Phone #:
Fax #:
Pager #:
PBX technician: |  | Phone #:
Fax #:
Pager #:
Distributor name:
Distributor contact: |  | Contact phone#:
Address: |  | Fax#:
City: |  | Pager#:
State and Zip: |  | e-mail address:
SDS name: |  | Contact phone#:
Completed by home office
Field Service rep: |  | Phone #:
NT coordinator: |  | Phone #:
Fax#:
Completed by home office
Pre-site date
Switch installation completion date
Avaya CallPilot® completion date (if different)
Date equip. shipping from Avaya facility to distributor/customer
Date technician on-site to begin installation

## Action Log
Installation Coordination Follow Up: Issues and Actions
Schedule 1st conference call with all involved parties. |  |  |  | Date:
Chairperson #: | Date of Conference Call: |  |  | Time of Call:
Participant #: |  |  |  | Number of Ports:
Attendees:
Issues from call #1: |  |  | Assigned To: |  | Date to Complete:
Schedule 2nd conference call with all involved parties for followup as required. |  |  |  | Date: | / /
Chairperson #: | Date of Conference Call: | / / |  | Time of Call: | :
Participant #: |  |  |  | Number of Ports:
Attendees:
Issues from call #1: |  |  | Assigned To: |  | Date to Complete:

## Info Summary
Information Summary | [8 empty] | Date of |  | Coordination
[9 empty] | Availability |  | Checkoff
For customer/switch tech duties see | Site Preparation
1. What kind of Switch is being used? |  |  |  | M1 Option 11C |  |  |  | Date: | / /
M1/CS 1000 - X11 software, release 25.40 or higher |  |  |  | M1 Option 11C Mini
M1 Option 51C
M1 Option 61C
M1 Option 81/81C
Communication Server 1000
SL-100 - software release, SL10 or higher |  |  |  | SL-100 (CS 2100)
DMS-100 - software release, NA08 or higher |  |  |  | DMS-100
IP address of switch
202i
2. Which model of Avaya CallPilot® server is being ordered? |  |  |  | 600r
1005r
1006r
1002rp
|  |  |  | (AC or DC version?) |  | AC | DC
3. What Avaya CallPilot software release was ordered?
4. All reference material and documentation of the above release reviewed prior to installation?
For CallPilot reference documentation go to: |  | Avaya Documentation
Meridian Mail Migration | [8 empty] | Date of |  | Coordination
[9 empty] | Availability |  | Checkoff
Refer to Avaya Meridian Mail to Avaya CallPilot® Migration Utility Guide (NN44200-502).
[6 empty] | Yes | No
5. Will Meridian Mail be migrated over to CallPilot? | [7 empty] | Date: | / /
(WARNING: users with Personal COS will not migrate)
| Meridian Mail # of Ports | [6 empty] | Meridian Mail # of Hours
| Meridian Mail # of Nodes | [6 empty] | Meridian Mail # of Users
6. Which version of Meridian Mail is currently installed? | [5 empty] | Must be version 11 or later to be migrated
7. CallPilot 1005r/1006r/600r server: Is there an SLR75 tape drive & cable available | [5 empty] | Yes | No
(or ordered) for connection to the CallPilot server? | [7 empty] | Date: | / /
The tape drive is used to read Meridian Mail tapes.
8. Callpilot 202i and 1006r: Is there a USB tape drive available. If you are using a SCSI
tape drive, is there a SLR75 tape drive and USB to SCSI adaptor available?
CLAN Readiness | [8 empty] | Date of |  | Coordination
[9 empty] | Availability |  | Checkoff
8. Does customer currently have a functional LAN? |  |  |  |  | Yes | No
[8 empty] | Date: | / /
9. When will the CLAN drop for CallPilot be available? | [7 empty] | Date: | / /
10. Twisted Pair Network cable from Server to CLAN Hub or |  |  |  |  | Yes | No |  |  | Length reqd:
ethernet switch available?
11. Which LAN Access Method are you using? | [6 empty] | Ethernet
12. What is the CLAN Ethernet LAN speed? |  |  |  |  | 10 MB/s
202i and 1002rp supports 100BaseT. |  |  |  |  | 100MB/s
600r, 1005r, 1006r support 1000BaseT. |  |  |  |  | 1000MB/s
13. What kind of Ethernet cabling will be used? |  |  |  | UTP |  | CLAN requires UTP/STP cabling
14. Is TCP/IP protocol currently installed and operating on the network? |  |  |  |  | Yes | No |  | Date: | / /
Server Hardware/Software Configuration Readiness | [8 empty] | Date of |  | Coordination
[9 empty] | Availability |  | Checkoff
15. What is the TCP/IP Network Information for the Server:
|  |  |  | CLAN Server IP Address: |  |  |  |  | (Must be unique on network)
|  |  |  | CLAN Subnet Mask: |  |  |  |  | (format ###.###.###.###)
|  |  |  | CLAN Default Router/Gateway Address (as required): |  |  |  |  | (format ###.###.###.###)
16. What is the Internet Domain Name? | [7 empty] | DNS IP address:
DNS IP address:
17. What should the CallPilot Server Windows 2003 Domain Name be?
(Optional)
18. What should the CallPilot Server Windows 2003 Computer Name be?
19. What should the CallPilot Server Windows 2003 Workgroup Name be? | [5 empty] | WORKGROUP |  |  | (default=WORKGROUP)
20. The Customer must provide 2 IP addresses for Remote Access Services (RAS) (for dial-in support)
If these IP addresses are on the same CLAN subnet as the Server, it is preferable to be in sequence.
|  |  |  | First RAS IP Address: |  |  |  |  | (Must be unique on network)
|  |  |  | Second RAS IP Address: |  |  |  |  | (Must be unique on network)
[6 empty] | Yes | No | Date: | / /
21. Is an analog DID line available for the remote maintenance modem?
Phone #
22. How many channels was the CallPilot Server ordered with? |  |  |  |  | Voice |  |  | (requires 1 MPU/channel)
[5 empty] | Multimedia (Fax) |  |  | (requires 2 MPU/channel)
[5 empty] | Speech Recognition |  |  | (requires 4 MPU/channel)
AppBuilder Client PC Readiness | [8 empty] | Date of |  | Coordination
[9 empty] | Availability |  | Checkoff
Refer to Avaya CallPilot® Application Builder Guide (NN44200-102).
Customer must supply a PC Client for testing purposes
23. Customer supplied PC Client have the following recommended requirements? | [7 empty] | Date: | / /
[6 empty] | Yes | No
Pentium 90 MHz (or faster)
Windows 98, Windows 2000 Professional, NT 4.0, XP or Vista
32 MB RAM (or more)
25 to 30 MB Disk free space for the Application Builder software
CD-ROM reader
Internet Explorer 5.5 SP2, 6.0 and 7.0
24. The CallPilot AppBuilder client is located on the CLAN.
Desktop Messaging PC Readiness | [8 empty] | Date of |  | Coordination
[9 empty] | Availability |  | Checkoff
Refer to Avaya CallPilot® Desktop Messaging and My CallPilot Installation & Administration Guide (NN44200-305)
Note: Customer must supply a PC Client for testing purposes
Desktop Messaging gives mailbox users access to their CallPilot messages from their PC e-mail.
[6 empty] | Yes | No
25. Did customer purchase Desktop Messaging?
26. Is Customer supplied PC Client available with the following recommended requirements?
This could be the same as the Admin Client PC. | [5 empty] | Yes | No | Date: | / /
486 or faster
Win 2000 Professional, Win XP Professional, Windows Vista
Linux OS (Mozilla 1.7x, Mozilla Firefox 2.0)
32 MB RAM
15 MB Disk free space
CD-ROM reader
Ethernet LAN card connection to the CLAN
27. Which E-mail software utilized & is it at the minimum release? | [5 empty] | Yes | No | Date: | / /
Microsoft Exchange v6.0
Microsoft Outlook 2002 (XP), 2003 or 2007
Lotus Notes 6.0, 6.5 and 7.0
Novell Groupwise 6.5 and 7.0
Microsoft Internet Explorer (Web Messaging/My CallPilot Only) 6.0 and 7.0
Microsoft Outlook 2002 XP, 2003 and 2007
Microsoft Outlook Express 6.0 or 7.0
28. What is the SMTP/VPIM Prefix?
(PSTN recommended)
Facility Readiness | [8 empty] | Date of |  | Coordination
[9 empty] | Availability |  | Checkoff
29. Is space available for the CallPilot server and peripherals? | [5 empty] | Yes | No
Room must also be available for technicians to access equipment. | [7 empty] | Date: | / /
Location of 202i server:
Two consective card slots must be available in the IPE shelf. Space must also | [5 empty] | Yes | No
be available for an external tape drive and CD-ROM.
Location of TRP server:
1005r, 1006r, and 600r - Space must also be available for the | [5 empty] | Yes | No
external tape drive or Tandberg RDX drive
30. Are you ready to maintain the site? | [5 empty] | Yes | No
- Who is maintaining the site?
- How are you going to be performing backups on the system? |  |  |  | Network Drive
Tape
[6 empty] | Yes | No
31. If 1002rp was ordered, was it ordered with the DC Power option?
32. Is dedicated AC Power within 6 feet of proposed 1002rp/1005r/1006r/600r | [5 empty] | Yes | No
server location? | [7 empty] | Date: | / /
Power receptacle needed for Server, 202i, Monitor, Modem (1002rp), external tape drive (1005r and 1006r) and possibly the Hub.
33. Does the environment support the physical and electrical requirements? | [5 empty] | Yes | No
[8 empty] | Date: | / /
|  | 1002rp | 1006r | 1005r |  | 600r
| Server Height (inches) | 12.5" | 3.44 | 3.45 |  | 1.75
| Server Width (inches) | 19 " | 17.77 | 17.14 |  | 17.5
| Server Depth (inches) | 19.25" | 33 | 20 |  | 20
| Server Current draw | 15A | 15A | 15A |  | 15A
| Server Weight (lbs) | 75 | 67 | 44 |  | 23
| AC Power Receptacles required * | 4 | 5 | 5 |  | 5
| DC Power connections | 1 (DC version only)
* receptacles required for peripheral devices
34. Will the following environmental specs be met at Server's location? | [5 empty] | Yes | No
Humidity: | 85% non-condensing at 104F | [6 empty] | Date: | / /
Temperature: | 50F to 95F derates .5F for every 1000ft
Altitude: | Less than 10,000ft
35. Is a 19" or 23" Rack ready for the 1002rp/1005r/1006r/600r Server? | [5 empty] | Yes | No
Note the large height of the 1002rp in the specifications above. | [7 empty] | Date: | / /
36. Delivery Instructions: | [5 empty] | Yes | No
Is there a docking facility at the Ship To location?
Is inside delivery required?
Training | [8 empty] | Date of |  | Coordination
[9 empty] | Availability |  | Checkoff
37. Will Avaya be providing on-site Basic Administrator and End User Training? | [5 empty] | Yes | No
[8 empty] | Date: | / /
- When should training occur?
- Lead Administrator contact name at site for coordinating training setup?
SL-100 (CS 2100)/DMS-100 Readiness | [8 empty] | Date of |  | Coordination
[9 empty] | Availability |  | Checkoff
Refer to <switch> and Avaya CallPilot® Server Configuration (NN44200-302, 303, 312) for switch programming requirements and procedures.
38. Switch Release | [5 empty] | Yes | No
SL-100 at Release SL10 or higher | [7 empty] | Date: | / /
DMS-100 at Release NA08 or higher | [7 empty] | Date: | / /
T1 lines are required for channel connectivity. |  | The SL-100 switch uses Line Side T1 cards or an external channel bank.
The DMS-100 switch requires an external channel bank.
39. Sufficient Line Side T1 cards (NT5D11) on SL-100? | [5 empty] | Yes | No
Every 24 CallPilot channels requires a Line Side T1 card in the SL-100. | [7 empty] | Date: | / /
Each Line Side T1 card in the switch supports one T1 link.
T1 cables (A0788107) required, otherwise a shielded cable must be used.
Line Side T1 cards MUST be configured for Ground Start. Loop Start is not supported on CallPilot.
40. Sufficient CallPilot Dialogic D/480JCT-2T1 cards ordered? | [5 empty] | Yes | No
(Each CallPilot Dialogic card supports 2 T1 Line Side cards - 48 channels) | [7 empty] | Date: | / /
41. T1 Link configuration parameters | [7 empty] | Date: | / /
Frame Format | D3/D4 | Required
Coding Format | B8ZS | Required
Cable Length | 0 | feet
Debounce Value | 13 | (recommended)
Hook Flash Time | 1 second | (recommended)
0
42. T1 Channel configuration parameters | [7 empty] | Date: | / /
There must be a Hunt Group configured on the switch for each media type
Voice Messaging UCD Hunt Group
UCD Hunt Group DN |  | This DN also goes in the CallPilot SDN table if Line DNs not used
Line DN |  | Forwarded to Group DNs (if used, this DN goes in CallPilot SDN table)
Channels |  | Which channels of which T1 Link
UCD Agent DNs |  | One agent DN per channel
Message Desk Number |  | First UCD group on a data link must be set to 63. Second is 62, etc.
Terminal Number |  | This is the unique ID assigned to each UCD agent.
Term Num starts at 1 (not 0) for the first channel.
Login |  | UCD agent login code.
Logout |  | UCD agent logout code
InDNLength |  | Internal DN length
FAX (Multimedia) Messaging UCD Hunt Group
UCD Hunt Group DN |  | This DN also goes in the CallPilot SDN table if Line DNs not used
Line DN |  | Forwarded to Group DNs (if used, this DN goes in the CallPilot SDN table)
Channels |  | Which channels of which T1 Link
UCD Agent DNs |  | One agent DN per channel
Message Desk Number |  | First UCD group on a data link must be set to 63. Second is 62, etc.
Terminal Number |  | Unique ID assigned to each UCD agent
Term Num starts at 1 (not 0) for the first channel
Login |  | UCD agent login code
Logout |  | UCD agent logout code
InDNLength |  | Internal DN length
Speech Recognition UCD Hunt Group
UCD Hunt Group DN |  | This DN also goes in the CallPilot SDN table if Line DNs not used
Line DN |  | Forwarded to Group DNs (if used, this DN goes in the CallPilot SDN table)
Channels |  | Which channels of which T1 Link
UCD Agent DNs |  | One agent DN per channel
Message Desk Number |  | First UCD group on a data link must be set to 63. Second is 62, etc.
Terminal Number |  | Unique ID assigned to each UCD agent
Term Num starts at 1 (not 0) for the first channel.
Login |  | UCD agent login code
Logout |  | UCD agent logout code
InDNLength |  | Internal DN length
SL-100/DMS-100 Data Link | [8 empty] | Date of |  | Coordination
[9 empty] | Availability |  | Checkoff
0
One SMDI data link is required between the COM 2 port on the CallPilot server and the MPC port on the switch.
[6 empty] | Yes | No | Date: | / /
43. Does the SL-100 have either a: |  |  |  | IOC Shelf
Requires an NT1X89 card (NTFX30AA). |  |  |  | IOM
InReach TS
44. If a direct SMDI cable connection will be used, the following distance limitations must be adhered to.
| IOC Shelf |  |  | Max 50 feet
Requires a NT0X96HJ or NT0X96EH IOC cable and a
customer supplied DB9F to DB25F Null Modem Cable.
| IOM |  |  | Max 750 feet
Requires a NT0X96LU IOM cable for a non-bulkhead or
NTRX26GA for a bulkhead type. Smart Connector (NTFX34AA),
and a customer supplied DB9F to DB25F Null Modem Cable.
| InReach |  |  | TBD
45. If a SMDI modem connection will be used, the following are the requirements: | [7 empty] | Date: | / /
| IOC Shelf |  |  | 2 General DataComm VF 28.8 modems (A0620530),
a customer supplied 2-wire private-line connection
between the two modems, one modem cable, a
NT0X96HJ or NT0X96EH IOC cable.
| IOM |  |  | 2 General DataComm VF 28.8 modems (A0620530),
a customer supplied 2-wire private-line connection
between the two modems, one modem cable, an IOM
cable (see direct connect), and a Smart Connector (NTFX34AA).
| InReach |  |  | TBD
46. SMDI Configuration parameters:
(Defaults will wait 50 seconds (10 seconds x 5) without a response from the polling signal before declaring that the SMDI link or the switch is down) | [6 empty] | Poll Timeout | 10000 |  | ms
(default = 10,000)
[7 empty] | Poll Timeout Threshold |  | 5
(default = 5)
[7 empty] | MWI Padding |  | 0
[7 empty] | Poll DN |  | 0 | Required
47. Addition of # and * to CallPilot for UCD Login/Logout Codes required? | [5 empty] | Yes | No
[8 empty] | Date: | / /
► CallPilot supports only digits 0 - 9, as indicated in the I&C guide ► Default SL-100 UCD login/logout codes are prepended with a * or # ► If CallPilot does not support * and # for the login/logout codes. An extra step is needed in SL-100 datafill to replace the * and # with a numeric sequence (typically 11 & 12) ► However, specific sites may have a conflict if they are using a public dial plan numbering scheme. In this case the datafill becomes more intense but is still achievable. default login = * + xxxx, default logout = # + xxxx CallPilot expects: login = yy+xxxx, logout = zz+xxxx Note: x, y, z = any number Star (*) and Pound (#) signs are seen as basic DTMF tones that are used on a regular basis. Distributor Translations Primes need to make the required changes related to the customer.
Web Messaging (My CallPilot) Readiness | [8 empty] | Date of |  | Coordination
[9 empty] | Availability |  | Checkoff
Refer to Avaya CallPilot® Desktop Messaging and My CallPilot Installation and Administration Guide (NN44200-305)
48. Is there a Web Server available to support My CallPilot? | [5 empty] | Yes | No
Avaya recommends this Web Server is dedicated to CallPilot Web Messaging. | [7 empty] | Date: | / /
49. Is Customer supplied Web Server available with the following minimum recommended hardware requirements?
[6 empty] | Yes | No | Date: | / /
Pentium 166 MHz (450 MHz recommended)
64 Mbytes RAM (128 Mbytes recommended)
150 Mbytes of Disk Free Space
50. Is Customer supplied Web Server available with the following recommended software requirements?
[6 empty] | Yes | No | Date: | / /
Windows 2003
MS Internet Inf. Server (IIS) version 6.0
51. Will Avaya be installing the My CallPilot software on the Web Server? | [7 empty] | Date: | / /
Installation requires reboot of the Web Server. | [5 empty] | Yes | No
52. Do the customer supplied PC Clients accessing My CallPilot meet the following requirements?
[6 empty] | Yes | No | Date: | / /
Win 2000 (Professional), WIN XP Professional, Windows Vista
One of the following supported Internet Browsers
Microsoft Internet Explorer 6.0 and 7.0
Mozilla 1.7.x and Mozilla FireFox 2.0
Microsoft Internet Explorer 5.1 on Macintosh OS 9
Microsoft Internet Explorer 5.2 on Macintosh OS X
JavaScript and Cookies must be enabled on the Browser
CallPilot Player or the Microsoft Media Player
(used for voice message playback)
Third party software to display TIFF-F files
(required for fax display and printing)
Messaging Networking Readiness | [8 empty] | Date of |  | Coordination
[9 empty] | Availability |  | Checkoff
Refer to Avaya CallPilot® Network Planning Guide (NN44200-201)
53. What type of Messaging Networking will be used by this CallPilot system | [7 empty] | Date: | / /
to network to other Mail systems?
|  |  |  | None |  |  | If None, skip all Networking Pages
|  |  |  | Network Message Service (NMS) |  |  | Not required for SL100 connectivity
|  |  |  | Integrated AMIS |  |  | Select all which are used
|  |  |  | Open AMIS |  |  | (could be more than one)
Enterprise
VPIM
[6 empty] | Yes | No
54. Is there a Messaging Networking Diagram available? | [7 empty] | Date: | / /
55. After the Messaging Networking diagram has been obtained, all the networking info must be obtained.
Complete sheet 1, Msg Net Readiness
Directory Synchronization Readiness | [8 empty] | Date of |  | Coordination
[9 empty] | Availability |  | Checkoff
Refer to Avaya CallPilot® Administrator Guide (NN44200-601)
Note: This information must be supplied by the Active Directory Administrator.
56. Is there an Active Directory Server on the LAN? | [5 empty] | Yes | No
[8 empty] | Date: | / /
57. Active Directory Server Type |  |  |  | Windows 2000
Windows 2003
58. An account on the Active Directory server with appropriate permissions
59. Fully Qualified Domain Name (FQDN) of the active directory Server
60. Active Directory LDAP suffix: (not required if same as FQDN)
61. Active Directory LDAP port number
62. If the Active Directory server is using SSL, what is the SSL port number?

## 1. Msg Net Readiness
Messaging Networking Readiness | [5 empty] | Date of | Coordination
[6 empty] | Availability | Checkoff
1. Prime Location Properties: |  | LOCAL Site Name
Prime Switch Location Name (can be same name as above)
Dialing Plan for dialing to this location: ESN
CDP
Hybrid combining ESN and CDP
If ESN, ESN Access Code
|  | If ESN, ESN Location Codes |  |  | Overlap
Overlap
|  |  | If more than 2, use |  |  | sheet 2, ESN
|  | If CDP, CDP Steering Codes |  |  | Overlap
Overlap
|  |  | If more than 2, use |  |  | sheet 2, CDP
|  | If VPIM, VPIM Network Shortcuts |  |  | Overlap
Overlap
|  |  | If more than 2, use |  |  | sheet 2, VPIM
2. Message Delivery Parameters
To accept the default, leave entry blank. |  | Batch Threshold |  |  | Default= 4 (messages)
|  | Economy Start Time |  |  | Default =6pm
|  | Economy Stop Time |  |  | Default= 6am
|  | Stale Time for Urgent Messages |  |  | Default= 60 (mins)
|  | Stale Time for Standard Messages |  |  | Default= 2 (hours)
|  | Stale Time for Economy Messages |  |  | Default= 23:59
|  | Holding Time for Standard Messages |  |  | Default = 40 min (calculated internally)
|  | Holding Time for Urgent Messages |  |  | Default = 6 min (calculated internally)
|  | Business Days |  |  | Default= Monday through Friday
|  | Non-business Days |  |  | Default= Saturday and Sunday
|  | Business Day Hours |  |  | Default= 9 am - 5 pm
|  | Non-business Hours |  |  | Default= 5 pm - 9 am
|  | Networking Loopback Mailbox |  |  | (used for testing)
Inbound Service Directory Number
Outbound Service Directory Number
Phantom DN
CDN
Remote Site Information | [5 empty] | Date of | Coordination
[6 empty] | Availability | Checkoff
3. If using Open AMIS Networking or Integrated AMIS Networking, what is the LOCAL:
AMIS Compose Prefix
Local System Access Number
Minimum number of Channels required on Avaya CallPilot®
Maximum number of Channels required on Avaya CallPilot
- - - - - - REMOTE SITE INFO - - - - - - -
List sites that exchange messages with this site using Integrated AMIS
Remote Site Name | Type | Connection DN1 |  | DN2 optional |  | DN3 optional
| If more sites exist, use | sheet 3, Remote site info
4. For Enterprise Networking: |  | Enterprise Site ID
Site name
|  | Fully Qualified Domain Name |  | (only if VPIM Networking is installed)
(HostName.DomainName)
- - - - - - REMOTE SITE INFO - - - - - - -
List sites that exchange messages with this site using Enterprise Networking or AMIS
Remote Site Name |  | Server Type |  |  |  | Site ID
| If more sites exist, use | sheet 3, Remote site info
5. For VPIM Networking: |  | Fully Qualified Domain Name (FQDN)
(HostName.DomainName)
Local Site name
Outgoing SMTP/Mail Proxy Server Address
VPIM Compose Prefix
- - - - - - REMOTE SITE INFO - - - - - - -
List sites that exchange messages with this site using VPIM
Remote Site Name | Type | Connection DN1 |  | DN2 optional |  | DN3 optional
| If more sites exist, use | sheet 3, Remote site info

## 2. ESN, CDP & VPIM
ESN Information
Complete this table if the local switch uses ESN or a hybrid (combination ESN and CDP) dialing plan
ESN Access Code
| Location code | Overlap
If there is an overlap between the
right-most digit or digits of
the location code and the left-most
digit or digits of the extension number,
enter the amount of overlap.
CDP Information
Complete this table if the local switch uses CDP or a hybrid (combination CDP and ESN) dialing plan
| Steering code | Overlap
If there is an overlap between the
last digit or digits of the steering
code and the first digit or digits
of the extension number,
enter the amount of overlap.
VPIM Shortcuts
| Prefix | Overlap

## 3. Remote site info
Enterprise Networking remote site information
Complete this table for all sites that exchange messages with this site using Enterprise Networking or AMIS
Remote site name |  |  | Server type |  | Site ID
Integrated AMIS and VPIM remote site information
Complete this table for all sites that exchange messages with this site using Integrated AMIS
Remote site name | Type | Connection DN1 |  | DN2 optional | DN3 optional

## 4.Site Preparation
Site Preparation
These steps are required to prepare the customer site to accept Avaya CallPilot®. It is the responsibility of the customer and/or the switch distributor/maintenance provider to ensure these steps are completed prior to installation of the server. Refer to the appropriate technical documents as required.
Avaya CallPilot AML Systems
Refer to NN44200-302 Meridian 1 and Avaya CallPilot® Server Configuration or NN44200-312 Avaya Communication Server 1000 and Avaya CallPilot® Server Configuration
Configure the switch
1. Make sure the switch X11 software is at a minimum Release 25.40 with patches.
2. Configure and enable the ELAN (Ethernet software) in the switch.
3. Configure the switch IP address.
4. Configure the customer data block for CallPilot.
5. Configure the ACD agent queue and agents.
6. Configure the voice-messaging CDN in the switch.
7. If the FAX option has been ordered, configure the FAX-messaging CDN in the switch.
8. Configure two phonesets for test purposes.
9. Verify the IOP, IOP/CMDU, or IODU/C card is installed in the switch.
Configure the connectivity hardware
This step is not applicable to the 201i server.
1. If your server is a tower or rackmount server, install the MGate card (NTRB18CA) in the switch. Note: This step is not applicable for the 201i or 202i IPE servers.
2. Meridian 1, Option 51C-81C
Connect the Ethernet AUI cable NT7D90DA from each IOP card to the I/O panel on the Meridian 1 switch..
3. Meridian 1, Option 11C
a. Install the transceiver cable (NT630723) on the bulkhead.
b. Attach the transceivers to each AUI connector for ELAN.
4. Install the ELAN hub.
5. Install and attach the Ethernet cable from the transceiver to the ELAN hub.
6. Install the Ethernet cable from ELAN Hub and have it ready to be connected to CallPilot.
7. Configure the ELNK (Ethernet) hardware in the switch.
8. Configure and enable the ELAN (Ethernet software) in the switch.
9. Have a connection from the CLAN to the CallPilot server available.
CallPilot T1/SMDI Systems
Refer to NN44200-303 T1/SMDI and Avaya CallPilot® Server Configuration
Configure the switch
1. Ensure Switch software release is supported. DMS - NA08 or higher, SL100 - SL10 or higher.
2. Configure DMS-100 or SL-100 switch software.
Configure the connectivity hardware
1. Ensure the NT1X89 card is available in the IOC shelf, or an IOM for SMDI link connection.
2. DMS-100
a. Ensure enough Line cards available for UCD agents. 1 card for each CallPilot channel.
b. Connect D/480JCT-2T1 cards to the channel bank.
3. SL-100
Connect D/480JCT-2T1 cards to the line side T1 cards.
4. Connect the SMDI cable directly (or by modem) to the IOC or IOM
5. Have a connection from the CLAN to the CallPilot server available.
General information for CallPilot
The customer must have functional LAN and a LAN connection available for the CallPilot before installation will take place.
The Meridian switch must be properly configured and upgraded prior to start of installation.
The customer needs to order the blank cartridge tapes they will need for backups on the CallPilot.
The customer or distributor needs to purchase PCAnywhere and install it on a remote PC if CallPilot is to be remotely supported.
Miscellaneous information
1. Are two phones available for testing purposes?
- If you only have the TN, get the DN by opening the overlay LD 20. Choose PRT, type TNB, and then enter the TN.
2. X11 Packages Required - LD22, TYP=PKG or PKG package# (i.e. PKG 77)
| 41 - ACDB (ACD Package B) | 46 - MWC (Message Waiting Center)
| 214 - EAR (Enhanced ACD Routing) | 215 - ECT (Enhanced Call Treatment)
| 218 - IVR (Hold in Queue for IVR) | 247 - (Call ID)
324 - MAS (MAS Connectivity)
Package 324 dependencies
| 77 - CSL (Command Status Link) | 153 - X25AP (Application Module Link -- AML)
| 164 - LAPW (Limited Access to Overlays) | 242 - MULI (Multi User Login)
| 243 - Alarm Filtering | 296 - MAT (Meridian Administration Tool)
| 364 - NMCE (CallPilot) | 254 - PHTN (Phantom TN)
Not required, but needed for additional functionality
| 98 - DNIS (Dialed Number Identification Service) | 113 - IDC (Incoming DID Digit Conversion)
| 207 - NACD for networking | 209 - MLM (Meridian Link Module) for MLink on CallPilot
3. These FAX features can be configured on CallPilot
a. Express Fax Messaging: callers who want to send a fax can call one standard number, enter the user's mailbox number and
press pound sign. The fax goes to the user's mailbox.
b. Virtual FAX DNs: Each mailbox owner gets a separate Fax DN. Callers dial directly and immediately get fax tone.
The fax goes directly to the user's mailbox. WARNING: ensure you have enough DNs and TNs for this on the switch (LD 10 or LD 11).
c. Multimedia Call Answering: Users can receive voice or fax message on the telset DN. This option
requires a CallPilot fax channel (2 MPUs) for each call that goes to CallPilot regardless of whether it is a voice or fax call.
The user will not know if the phone is ringing for a fax or voice call.

## 5. Web Server Config
Avaya CallPilot® Web Server Configuration
Introduction
Avaya CallPilot 5.0 has three web services. Each web service uses Microsoft IIS.
a) CallPilot Manager - installed on the CallPilot Server (can also be installed on an external web server). b) Reporter - must be installed on an external web server. c) My CallPilot - can be installed on both the CallPilot Server and an external web server.
CallPilot Web Server Configurations
1. All three web services on External IIS Server - Recommended
This configuration provides better security. The customer's IT department can manage and apply the latest IIS security updates to the server. The IIS on CallPilot can be disabled altogether and thus remove a target for a hacker attack. NOTE: Although the IIS on CallPilot is pre-configured with the best security updates available, if it is not needed, disabling it on CallPilot completely shuts the door to attacks on IIS.
2. Hybrid
a) My CallPilot on CallPilot server b) CallPilot Manager and Reporter on External IIS Server
Notes:
1. CallPilot Reporter cannot be installed on the CallPilot server. The “bursty” CPU loads from running reports are inconsistent with CallPilot server's mission as a real-time application environment. 2. When CallPilot Reporter is configured on an external IIS server, CallPilot Manager is also installed. 3. CallPilot Manager and My CallPilot can be installed on both CallPilot and the external IIS server, although this is not the recommended configuration.
CallPilot comes pre-engineered to support My CallPilot and/or CallPilot Manager IIS web services and still provide high service levels to all other services running on CallPilot. End-user and administrator web browsers access the IIS server on CallPilot via the CallPilot IP address on the CLAN. There are no additional engineering considerations. However, as noted above, if there are no web services running directly on CallPilot, the IIS server can be disabled to increase security.
External Web Server Configuration
The external web server, which hosts the CallPilot web services, networks to the CallPilot server via CallPilot's IP address on the CLAN.
Hardware
Because web messaging through My CallPilot and Reporter web services can generate high CPU loads, the minimum recommended hardware configuration for the external web server is:
a) 600 MHz PIII system b) 128 Mbytes of RAM c) 1 Gbyte of disk space
Software
Software the external web server requires:
a) Windows 2000 server with IIS 5.0 (Advanced Server, DataCenter Server not supported) or b) Windows 2003 server with IIS 6.0
If SSL is to be used, you need to purchase and install an additional IIS certificate. Avaya recommends Entrust or Verisign.
Free disk space
There should be 1 GByte of free disk space on the server before installing the CallPilot web services. If the Reporter service is going to be used for a large CallPilot system or a network of CallPilot systems, it is recommended that the free disk space be estimated using the following formula.
Free Disk Space = 300MB + (Total # of Channels * (Days in DB + 1) * 0.2 MB) where:
- total C52 of channels is the total number of channels on all CallPilot systems whose data is in the Reporter database. - days in DB is the number of days data will be stored in the Reporter database.
Engineering the server
The following factors drive the web server load from CallPilot services.
- number of users of My CallPilot - number of users accessing messages from My CallPilot versus using desktop messaging clients such as Outlook. - number of reports generated during busy hours
The server does not have to be dedicated to CallPilot web services, but it is recommended. The same server can host other web pages or also provide standard network services, such as printing and file sharing. However, running other applications and services on the server can cause slow response levels for CallPilot services that would significantly lower user productivity and satisfaction with the services.
Monitoring performance
As with any web server, the performance should be monitored following an installation or major change, such as adding more users to check for possible system overload. If response time is slow during the busy hour, you can monitor the level of activity on the web server to see if it is overloaded. Windows Performance Monitor can provide this information. The two main indicators to monitor are CPU usage and available memory. If the CPU usage (shown as Processor Time) is constantly above 90 percent for a number of minutes during the busy hour and/or memory availability (shown as Available Bytes) is ever below 4 Mbytes, then user response time is likely degraded.
Supported Web Browsers
CallPilot web services can be accessed from a Windows PC with Netscape 6.2 or higher or Internet Explorer 6.0 or higher web browser.
Application Builder
The administrative service, Application Builder, that is used to build voice menus, auto attendant application services, still requires a client to be installed on the administrator's PC. However, the client can be downloaded, on demand, onto the PC from CallPilot Manager web service.

## 6. Desktop Messaging
Avaya CallPilot® Desktop Messaging
PC Requirements
Avaya CallPilot is compatible with:
Windows 2000 Professional
Windows XP Professional
Clients
Software requirements for Desktop Messaging clients:
Desktop Messaging for Microsoft Outlook
Microsoft Outlook 2002 (XP)
Microsoft Outlook 2003
Microsoft Outlook 2007
Desktop Messaging for Lotus Notes
Lotus Notes versions 6.0, 6.5 and 7.0
Desktop Messaging for Internet Mail clients
Microsoft Outlook 2002 (XP)
Microsoft Outlook 2003, 2007 (in internet mode)
Microsoft Outlook Express 6.0
Windows Vista Mail
Desktop Messaging for Novell GroupWise
Groupwise 6.5 and 7.0
Windows Messaging 4.0 (Note: Networking TCP/IP must use Microsoft protocol stack in Novell Netware network. The disk space required for the software is 20 Mb.)
Desktop Messaging for Web Browsers
Microsoft Internet Explorer 6.0 and 7.0
Mozilla Firefox 2.0 for Windows
For Macintosh: Safari 1.x for Macintosh OS X
For Linux: Mozilla 1.7.x, Mozilla Firefox 2.0
Disk storage for messages
CallPilot uses a proprietary sub-band voice encoding at 18 Kbps. To calculate the storage used for voice in the CallPilot message store of desktop messaging, use the following conversion factor.
141 Kbytes = 1 minute of voice (SBC or VBK)
Note: Messages are kept in the message store on the PC only if they are played via the PC. If a voice message is converted and saved to disk as WAV, then use: 945 Kbytes = 1 minute of voice (WAV)
For more information on the Desktop Messaging software available with CallPilot, refer to the Desktop Messaging User Guides. For more information on the Desktop Messaging PC, refer to the Desktop Messaging and My CallPilot Installation and Administration Guide (NN44200-305).

## 7. High Availability
Avaya CallPilot® High Availability
Introduction
Use the following table to plan and track the system settings for your High Availability servers. These settings are configured using the Avaya CallPilot Configuration Wizard and the High Availability Configuration Wizard.
The High Availability feature is only available on 1005r servers with AML connectivity.
For more information on High Availability, refer to the High Availability: Installation and Configuration guide (NN44200-311).
| CP Node 1 (CP1) | CP Node 2 (CP2)
Configuration Wizard: Serial Number and Keycode page
Serial Number
Keycode
Configuration Wizard: Server Information page
Computer Name Note: Must only include alphanumeric characters.
Time Zone
Area Code
Country Code
LDAP Search Base
Configuration Wizard: Password Information page
Administrator password Note: Both nodes must have the same password.
Configuration Wizard: Switch Information page
Switch Type
Switch Customer Number
Switch IP Address
Link1 TN
Link1 Key0
Link1 Key1
Link2 TN
Link2 Key0
Link2 Key1
Link3 TN
Link3 Key0
Link3 Key1
CDN
Configuration Wizard: Language Source Directory page
Primary language
Secondary language
Configuration Wizard: CallPilot Local Area Network Interface page
ELAN subnet IP address
ELAN subnet mask
Avaya server subnet (CLAN) IP address
Avaya server subnet (CLAN) subnet mask
Avaya server subnet (CLAN) gateway IP address
Heartbeat 1 (HB1) IP address
Heartbeat 1 (HB1) subnet mask
Heartbeat 2 (HB2) IP address
Heartbeat 2 (HB2) subnet mask
Mirror IP address
Mirror subnet mask
High Availability Configuration Wizard
Managed CLAN Host Name Note: The CLAN is the Avaya server subnet.
Managed CLAN IP address
Managed ELAN IP address Note: The ELAN is the ELAN subnet.
Node 1 Host Name
Node 2 Host Name
Number of MPB96 Boards
User Name Note: This is the administrator's user name.
Server Workgroup/Domain Name
EMC AutoStart Domain Name
CLAN Test IP